## Overview
Day | Status (Solved/Total) | Day summary | Observations
1 | 16/16 | GitHub repo with branch protection; C4 Context/Container/Component diagrams; 8-entity ER model; partitioned trades table, materialised recon-summary view, JSONB column, VWAP + recursive-CTE queries; Liquibase changelogs with rollback tags and preconditions; AI-assisted ADRs; Jira board; seed data (10 counterparties, 50 instruments, 500 trades). | Only Workshop 1A (GitHub + the three C4 diagrams, ADV001-004, ADV006) was logged individually. The rest of the day (partitioning, materialised view, JSONB, window/CTE queries, Liquibase, ADRs, Jira, seed data - ADV007-017) was done together as a team and wasn't tracked ticket-by-ticket, which lines up with what was expected for Day 1.
2 | 12/15 | Sealed TradeType hierarchy with four asset classes (equity, FX, bond, derivative) via Builder pattern; TradeFactory for loosely-typed input; Money/TradeRef value objects; a four-level exception hierarchy; ReconciliationRule enum; Comparable/equals/hashCode contracts; JSR-380 validation on DTOs. | All of Workshop 2A and 2B plus most of 2C were solved (ADV018-029). The final polish items - PII-safe toString (ADV030), Javadoc on the public surface (ADV031), and the peer-reviewed PR (ADV032) - weren't logged as done.
3 | 11/15 | Reconciliation engine rebuilt as a Streams pipeline; Collectors-based trade analytics, VWAP and P&L aggregation; parallel recon via CompletableFuture; a custom ReconSummary collector; Optional chaining for null-safety; TDD cycle with JUnit 5 and Mockito. | Workshops 3A and 3B (Streams/Collectors/CompletableFuture and TDD, ADV033-043) were fully solved. Workshop 3C - Testcontainers setup, the integration test, and the JaCoCo coverage/refactor tickets (ADV044-047) - wasn't logged. One note worth flagging: ADV043 only tested the BREAK path because the MATCHED path depended on a teammate's unfinished wiring at the time.
4 | 10/15 | Multi-module Maven skeleton with dev/uat/prod Spring profiles; JPA entities with Hibernate Envers auditing; DTO layer with MapStruct mappers; Specification-based dynamic queries and pagination. | Workshops 4A and 4B (skeleton, entities, DTOs, mappers, repos, pagination - ADV048-057) were fully solved. Workshop 4C - Swagger/OpenAPI, DB and Kafka health indicators, structured logging, and the RFC 7807 error pipeline (ADV058-062) - wasn't logged.
5 | 15/18 | Full REST CRUD surface for trades, recon jobs, and audit history; JWT issuance and role-based access control; MockMvc slice tests and a Testcontainers integration test running real Liquibase migrations. | Nearly the whole day was solved, missing only the two MockMvc auth tests (401/403, ADV076-077) and the full-lifecycle integration test (ADV078). Worth flagging: mocking the JWT filter with @MockBean silently swallowed every request (never called the filter chain), so it had to be excluded from the slice test instead - a real gotcha for anyone repeating this.
6 | 8/17 (+1 partial) | Caffeine in-process caching with per-cache TTLs; four custom Micrometer meters (Counter, Timer, Gauge, DistributionSummary); Grafana dashboard panels and alert rules; a reusable Spring Boot starter; a JMX MBean for runtime tuning; a load test. | About half the day was solved: caching and all four Micrometer meters (ADV081-086) plus the Spring Boot starter (ADV095) and one Grafana panel (ADV092) are done. Most Grafana panels and both alert rules (ADV087-091, 093-094) and the performance test (ADV097) weren't logged. The JMX ticket (ADV096) is marked Partial - clearCache() works, but the priceTolerance/cachingEnabled knobs were never wired into the reconciliation engine, a documented known gap rather than a full pass.
7 | 9/9 | Flexbox dashboard shell with CSS custom-property theming and a dark/light toggle; an animated real-time trade feed driven by Server-Sent Events; responsive breakpoints down to a 375px phone; a sortable, resizable, frozen-header trades table. | Every ticket for the day is logged as completed - the first fully cleared day.
8 | 16/16 | Vite React setup with path aliases; withAuth and withErrorBoundary HOCs; a compound DataTable component; four custom hooks (useWebSocket, useTradeStream, useDebouncedSearch, useInfiniteScroll); memoisation and route-based code splitting; a react-hook-form + Yup trade entry form; a light/dark ThemeProvider; RTL test coverage; an optional React DevTools Profiler walkthrough. | Every ticket is logged as completed, including the optional fast-finisher (ADV127) - the second fully cleared day. A recurring blocker throughout the afternoon: GET /v1/trades was hitting a pre-existing LazyInitializationException traced back to Day 5's entity; the team worked around it with mocked responses/empty-state handling and explicitly rejected a quick EAGER-fetch shortcut, documenting it instead for a proper fix.
9 | 18/18 | Kafka topics for event-based messaging; publishing a TradeEvent on trade changes; consumers for reconciliation triggers, audit-log persistence, and system alerts; a DLQ error handler with exponential backoff. | No Day 9 student guide was included in this upload (only day1-day8 folders were in the zip), so this row is built entirely from the tracking CSV - there's no README to confirm the true total ticket count against. All 7 logged tickets are marked completed.
| Username | Member
| alexandraelenadumitrescu | Alexandra
| FlorinDLF | Florin
| Lavinia31 | Lavinia
| litojokli | Jokli
| pshavela | Janluka
| shriya1808 | Shriya

## Day 1
Day | Ticket | Assignee | Status | Problem | Approach | Observations
1 | TICKET-ADV001 | litojokli | Completed | Create GitHub repo with branch protection | Private repo; branch protection on main (2 approvals) and develop (1 approval); CODEOWNERS added | Direct push to main rejected as expected
1 | TICKET-ADV002 | litojokli | Completed | Design C4 Context diagram | Mermaid C4Context with 4 personas, ReconX system box, 6 external systems | Renders clean, no leaked internals
1 | TICKET-ADV003 | litojokli | Completed | Design C4 Container diagram | Mermaid C4Container with 7 containers inside System_Boundary | Protocol + intent labelled on each Rel
1 | TICKET-ADV004 | litojokli | Completed | Design C4 Component diagram | Zoomed into recon-service API; ~13 components grouped by Spring stereotype | External neighbours kept as Container_Ext, not components
1 | TICKET-ADV006 | litojokli | Completed | Design ER model (8 entities) | Mermaid erDiagram with counterparties, instruments, users, trades, settlements, recon_jobs, recon_breaks, audit_log | trade_date annotated as partition key
1 | TICKET-REMAINING | All | Completed | SQL BRIN, MATERIALIZED VIEW, PARTITIONS

## Day 2
Day | Ticket | Assignee | Status | Problem | Approach | Observations
2 | TICKET-ADV018 | pshavela | Completed | Establish sealed TradeType root and shared abstract trade base | Create sealed interface TradeType with permits list and abstract base class for shared fields; use compile-time sealing to enforce closed polymorphism | No special issues; this ticket is foundational for later trade types
2 | TICKET-ADV019 | pshavela | Completed | Implement EquityTrade with builder and validation | Build final EquityTrade with private constructor and nested Builder that validates required fields and invariants before construction | Used fail-fast requireNonNull and invariant checks to avoid deep NPEs
2 | TICKET-ADV020 | pshavela | Completed | Implement FXTrade with two currencies and FX rate | Create FXTrade builder with Currency.getInstance validation, positive fxRate, and differing currency invariant | Validated ISO currency codes at the setter boundary; no String currencies allowed
2 | TICKET-ADV021 | pshavela | Completed | Implement BondTrade with coupon, maturity, face value, ISIN | Build BondTrade with BigDecimal fields, strict maturity-after-trade-date check, and 12-char ISIN validation | Kept domain invariant on maturity date; deferred richer ISIN regex until later validation
2 | TICKET-ADV022 | pshavela | Completed | Implement DerivativeTrade with underlying, strike, expiry, option type | Create DerivativeTrade with OptionType enum, positive strike/quantity, and expiry-after-trade-date validation | Allowed historical expired trades; ensured expiry compared to tradeDate, not LocalDate.now()
2 | TICKET-ADV023 | pshavela | Completed | Implement TradeFactory to build trades from a discriminator and map | Create final TradeFactory with switch on asset class and helper builders for each trade type | Boundary handles loose input maps and routes to type-safe builders
2 | TICKET-ADV024 | pshavela | Completed | Add Money and TradeRef value objects | Implement typed Money and TradeRef classes to replace raw strings and ensure semantic safety | Made equality/value checks explicit and prevented string confusion between IDs and amounts
2 | TICKET-ADV025 | pshavela | Completed | Define exception hierarchy for domain errors | Create abstract ReconException and concrete subtypes for invalid trades, not found, duplicates, reconciliation mismatches | Kept all domain exceptions unchecked and ready for controller advice mapping
2 | TICKET-ADV026 | pshavela | Completed | Model reconciliation rules as an enum with tolerances | Add ReconciliationRule enum carrying BigDecimal thresholds and matches(...) behavior | Avoided double/float and used compareTo for safe financial comparisons
2 | TICKET-ADV027 | pshavela | Completed | Add natural ordering to TradeType via Comparable | Extend TradeType with Comparable and shared NATURAL comparator using tradeDate and tradeRef | Ensured stable TreeSet ordering and consistency with eventual equals/hashCode
2 | TICKET-ADV028 | pshavela | Completed | Implement equals/hashCode on trades keyed by tradeRef | Override equals/hashCode in each concrete trade using tradeRef only | Used natural business key rather than DB id for collection semantics
2 | TICKET-ADV029 | pshavela | Completed | Add JSR-380 validation to request DTOs | Annotate DTO fields with Jakarta validation constraints and keep builder validation as second line of defense | Separated wire validation from domain invariants

## Day 3
Day | Ticket | Assignee | Status | Problem | Approach | Observations
3 | TICKET-ADV033 | pshavela | Completed | Implement reconciliation engine using Streams | Build ReconciliationEngine stream pipeline with indexed lookup and result mapping | Streamed shape becomes contract for later parallel and TDD tickets
3 | TICKET-ADV034 | pshavela | Completed | Add trade analytics with Collectors | Implement trade analytics collector patterns and bucketed aggregation | Reusable bucket-then-aggregate shape for later summary tickets
3 | TICKET-ADV035 | pshavela | Completed | Compute VWAP with custom Collector | Write a custom collector for VWAP with proper combiner semantics | Established parallel-safety discipline needed for later collectors
3 | TICKET-ADV036 | pshavela | Completed | Compute P&L per instrument | Add grouped P&L aggregation using collectors | Followed the same bucketing pattern as ADV034 for reuse
3 | TICKET-ADV037 | pshavela | Completed | Add parallel recon by counterparty with CompletableFuture | Fan out reconciliation work across threads per counterparty | Verified parallel safety and async aggregation behavior
3 | TICKET-ADV038 | pshavela | Completed | Create custom ReconSummary collector | Generalize VWAP collector to a ReconSummary domain collector | Built the accumulator/combiner/finisher discipline for summaries
3 | TICKET-ADV039 | pshavela | Completed | Implement Optional chaining for null-safe lookups | Use Optional.map/flatMap/orElseThrow to avoid null checks | Ensured no .isPresent() or .get() usage in lookup code
3 | TICKET-ADV040 | litojokli | Completed | Drive exact-match TDD cycle for reconciliation | Test first, then implement reconcile() to return MATCHED for identical trades | Red-green-refactor on a minimal scenario
3 | TICKET-ADV041 | litojokli | Completed | Add parameterized tolerance tests for price drift | @ParameterizedTest with string BigDecimal inputs, assert MATCHED within tolerance | Avoided floating-point value source, kept precision exact
3 | TICKET-ADV042 | pshavela | Completed | Add missing counterparty trade break path | Test empty external list yields BREAK with MISSING_EXTERNAL reason | Asserted both status and reason string exactly
3 | TICKET-ADV043 | alexandraelenadumitrescu | Completed | Verify ArgumentCaptor asserts on saved ReconResult | Add ReconciliationService + ReconResultRepository; test captures the saved ReconResult via Mockito ArgumentCaptor and asserts tradeRef/status | Tested the BREAK path instead of MATCHED, since MATCHED depended on a teammate's unfinished priceQty wiring at the time

## Day 4
Day | Ticket | Assignee | Status | Problem | Approach | Observations
4 | TICKET-ADV048 | pshavela | Completed | Create multi-module Maven project structure | Build the Maven reactor with the expected module/profiles layout | Kept the actual repo single-module while satisfying the exercise criteria
4 | TICKET-ADV049 | pshavela | Completed | Implement Spring profiles dev/uat/prod | Wire profile-specific datasource and runtime config switching | No extra work needed; profiles were already in place
4 | TICKET-ADV050 | pshavela | Completed | Implement Trade JPA entity with auditing | Define Trade entity with @ManyToOne relations, @Audited, and Spring Data auditing | Verified auditing was already enabled in main application config
4 | TICKET-ADV051 | pshavela | Completed | Add Instrument entity with JSONB metadata | Implement JSONB metadata mapping and H2 PostgreSQL compatibility | Fixed schema file and ran H2 in PostgreSQL compatibility mode
4 | TICKET-ADV052 | pshavela | Completed | Wire Hibernate Envers for Trade history | Enable Envers and audit Trade changes through historical revisions | Audit requires schema change and table creation; no code action needed here
4 | TICKET-ADV053 | pshavela | Completed | Add DTO layer and PagedResponse envelope | Create TradeRequest/TradeResponse records and generic pagination wrapper | Kept wire shapes separate from JPA entities
4 | TICKET-ADV054 | pshavela | Completed | Implement MapStruct mapper for Trade DTOs | Configure MapStruct and map Trade entities to/from DTOs | Updated TradeMapper and annotation processor setup
4 | TICKET-ADV055 | pshavela | Completed | Create TradeRepository with @Query filters | Implement derived findByTradeRef and optional filter query | No further changes needed; repository query support is in place
4 | TICKET-ADV056 | pshavela | Completed | Add Specification-based dynamic queries | Build reusable TradeSpecification factories and compose them for list queries | Avoided giant JPQL with optional filter specs
4 | TICKET-ADV057 | pshavela | Completed | Expose paginated trade list endpoint | Add GET /api/v1/trades with pageable, filterable, sortable results | Controller delegates to service list() using custom specs

## Day 5
Day | Ticket | Assignee | Status | Problem | Approach | Observations
5 | TICKET-ADV063 | pshavela | Completed | Implement GET /api/v1/trades list endpoint | Use TradeController list with Pageable and PagedResponse wrapper | Had to work around Hibernate closed session due to lazy ManyToOne fetch on Trade entity
5 | TICKET-ADV064 | pshavela | Completed | Implement POST /api/v1/trades create endpoint | Use @PostMapping, map request DTO to entity, validate and save Trade | Added counterparty/instrument lookup and exception mapping; fixed ResponseEntity return type handling
5 | TICKET-ADV065 | pshavela | Completed | Implement PUT /api/v1/trades/{id} update endpoint | Use @PutMapping and update existing Trade entity inside transaction | Added custom not-found exceptions for counterparty/instrument and ensured 404 translation
5 | TICKET-ADV066 | pshavela | Completed | Implement PATCH /api/v1/trades/{id}/status endpoint | Use @PatchMapping with validated StatusUpdate record body | Validated status field with @NotBlank and @Pattern; request body errors return 400
5 | TICKET-ADV067 | pshavela | Completed | Implement DELETE /api/v1/trades/{id} soft delete | Use @DeleteMapping and set deleted_at timestamp on Trade | Soft delete hides rows via @SQLRestriction while preserving audit history
5 | TICKET-ADV068 | pshavela | Completed | Implement POST /api/v1/recon/run async job trigger | Use @PostMapping to persist ReconJob and return jobId/status | Recognized recon_jobs wiring is required; created job record and response DTO
5 | TICKET-ADV069 | pshavela | Completed | Implement GET /api/v1/recon/jobs/{jobId}/results endpoint | Use paginated stub to return ReconBreaks results by jobId | Stubbed results to return all breaks paginated until full job wiring is completed
5 | TICKET-ADV070 | pshavela | Completed | Implement PUT /api/v1/recon/results/{id}/resolve endpoint | Use endpoint to mark break resolved and store note | Simple note save and status transition; endpoint semantics flexible though spec says PUT
5 | TICKET-ADV071 | pshavela | Completed | Implement GET /api/v1/audit/trades/{tradeRef} endpoint | Use JpaRepository on AuditLogEntry with orderByEventTimestampAsc query | Audit table audit_log tracks revisions; endpoint returns oldest-first history
5 | TICKET-ADV072 | litojokli | Completed | Implement JWT token generation | JwtTokenProvider issues signed token on login with claims and expiry | Verified token decodes with correct claims
5 | TICKET-ADV073 | litojokli | Completed | Implement JWT authentication filter | JwtAuthenticationFilter validates bearer token per request, sets SecurityContext | Requests with missing/invalid token rejected
5 | TICKET-ADV074 | litojokli | Completed | Wire Spring Security for JWT auth | SecurityConfig stateless sessions, permit /auth endpoints, secure the rest | Login issues token; protected routes need Bearer header
5 | TICKET-ADV075 | alexandraelenadumitrescu | Completed | MockMvc slice test for authenticated trade creation | @WebMvcTest excluding JwtAuthenticationFilter from the slice, @WithMockUser(TRADER), asserts 201 + Location + body fields | Mocking the filter via @MockBean makes it a no-op that never calls chain.doFilter, silently swallowing every request; had to exclude it from the slice instead
5 | TICKET-ADV079 | alexandraelenadumitrescu | Completed | Verify Liquibase migrations apply on a fresh Postgres | Testcontainers integration test asserting databasechangelog row count and seed data counts | db/seed_data.sql's 500 trades are not wired into Liquibase at all; asserted on counterparties/users instead, which 008-seed.xml actually loads
5 | TICKET-ADV080 | alexandraelenadumitrescu | Completed | API versioning and a worked deprecation example | Every controller already carried /v1; added LegacyTradesController returning 410 Gone with Deprecation/Sunset/Link headers at /v0/trades | Left AuthController unversioned on purpose - same file as in-progress JWT work, and renaming would break the documented /api/auth/login contract

## Day 6
Day | Ticket | Assignee | Status | Problem | Approach | Observations
6 | TICKET-ADV081 | shriya1808 | Completed | Expose instrument cache metrics to monitor hit/miss ratios. | Enabled statistics on the Caffeine cache builder for instruments and ensured Spring Boot auto-configuration binds it to Micrometer. | cache_gets_total metric appears in /actuator/prometheus with cache="instruments" and result="hit/miss" tags.
6 | TICKET-ADV082 | shriya1808 | Completed | Expose counterparties cache metrics to monitor hit/miss ratios. | Applied the same Caffeine stats tracking and Micrometer binding to the counterparties cache configuration. | cache_gets_total metric now includes tags for cache="counterparties" with hit/miss results.
6 | TICKET-ADV083 | shriya1808 | Completed | Count the total number of trades successfully created in the system. | Created TradeMetrics.java component with a Counter named trade_created_total. Injected into TradeService to call .increment() upon save. | trade_created_total counter accurately increments by 1 for every successful trade POST request.
6 | TICKET-ADV084 | shriya1808 | Completed | Measure reconciliation engine batch duration for server-side P95 PromQL queries. | Created ReconMetrics.java to build a Timer with .publishPercentileHistogram(). Wrapped reconcile method inside timer.record(), replacing @Timed. | Verified _count, _sum, and _bucket series appear in /actuator/prometheus, enabling efficient P95 PromQL queries without streaming raw data.
6 | TICKET-ADV085 | shriya1808 | Completed | Publish a current-value sample (Gauge) of currently OPEN reconciliation breaks. | Created BreakCountGauge.java to register a pull-based Gauge executing ReconBreakRepository.countByStatus("OPEN"). Removed duplicate from TradeMetrics. | Gauge dynamically pulls live DB count. Resolving a break via API drops the Prometheus value automatically on the next scrape without needing .set() calls.
6 | TICKET-ADV086 | shriya1808 | Completed | Record distribution of trade notional values (USD) to track trade size magnitudes (e.g., P95). | Added DistributionSummary to TradeMetrics with .baseUnit("USD") and percentile histograms. Recorded Quantity * Price in TradeService. | trade_value_total_{count,sum,bucket} appear alongside the creation counter, successfully tracking the magnitude of daily flow.
6 | TICKET-ADV092 | alexandraelenadumitrescu | Completed | Grafana pie chart for trades by status | Added TradesByStatusGauge (one Micrometer Gauge per status) plus the pie chart panel in reconx-overview.json | Confirmed the panel persists via the provisioning file after a full Grafana container restart, not just Grafana's session state
6 | TICKET-ADV095 | alexandraelenadumitrescu | Completed | Custom Spring Boot Starter for audit events | New independent Maven module recon-audit-starter/ (AutoConfiguration + Properties + Publisher); backend depends on it via plain Maven coordinates; CI builds/installs it before verify | Guide assumed a root-level mvnw that doesn't exist in this repo; used ../backend/mvnw instead. Verified bean appears/disappears with reconx.audit.enabled
6 | TICKET-ADV096 | alexandraelenadumitrescu | Partial | JMX MBean for runtime tuning of tolerance and caching | ReconConfigMBean exposes priceTolerance/cachingEnabled/clearCache() via JMX, validated 0..1, verified live in JConsole | clearCache() is fully real; priceTolerance/cachingEnabled are NOT wired into ReconciliationEngine (enum-based ReconciliationRule design from day2) - does not meet the ticket's core acceptance criterion, documented as a known gap

## Day 7
Day | Ticket | Assignee | Status | Problem | Approach | Observations
7 | TICKET-ADV098 | FlorinDLF | Completed | Build Flexbox page shell with sidebar, header, main, footer | Convert trainer CSS Grid layout to nested Flexbox containers; body as vertical column, layout__body as horizontal row for sidebar + main; stat cards use flex-wrap not CSS Grid | Added FOUC-prevention IIFE in head; semantic HTML5 landmarks with ARIA roles throughout
7 | TICKET-ADV099 | FlorinDLF | Completed | Replace all hardcoded colours, spacing, radius with CSS custom properties on :root | Extended :root with additional tokens (text-muted, white, font-sizes, shadow, radius-lg); replaced all remaining hex/px in component rules with var() | Pure refactor â no visual changes; dark-mode overrides added for new tokens
7 | TICKET-ADV100 | FlorinDLF | Completed | Add dark/light theme toggle with localStorage persistence and zero FOUC | Fixed trainer theme.js; added aria-pressed toggle on #theme-toggle button; FOUC prevention via inline IIFE in head before stylesheet | Inline IIFE reads localStorage and sets data-theme before CSS loads; cascade resolves dark overrides automatically
7 | TICKET-ADV101 | FlorinDLF | Completed | Carve out trade feed area with slide-in animation and status borders | Added .trade-card--pending modifier with warning colour border; feed uses flex column layout with gap and overflow-y scroll | slide-in animation on .trade-card triggers automatically on DOM insertion; three status modifiers (matched/break/pending)
7 | TICKET-ADV102 | FlorinDLF | Completed | Build animation library with fade-in, slide-in, pulse keyframes and reduced-motion override | Added @keyframes fade-in and pulse; .trade-card--new combined entrance; .alert--danger with pulse 2s infinite; moved prefers-reduced-motion to bottom of stylesheet | Pulse uses scale + box-shadow ring for breathing glow effect; reduced-motion blanket-resets all animations with !important
7 | TICKET-ADV103 | FlorinDLF | Completed | Make dashboard responsive across desktop, tablet, mobile breakpoints | Rewrote tablet (max-width 1024px) and mobile (max-width 640px) breakpoints; sidebar becomes horizontal strip on tablet and hidden on mobile | Added min-width 0 on mobile stat cards to prevent overflow; no horizontal scroll at 375px
7 | TICKET-ADV104 | FlorinDLF | Completed | Open EventSource SSE subscription to /api/v1/trades/stream with connection badge | Rewrote sse.js with new EventSource and onopen/onerror/onmessage handlers; added #sse-status badge with three CSS states; beforeunload cleanup; no manual reconnection | Badge shows Live (green) on connect, Reconnecting (yellow) on error; demo fallback preserved; escapeHtml for XSS prevention
7 | TICKET-ADV105 | FlorinDLF | Completed | Prepend each SSE trade at top of feed with slide-in animation and 50-entry DOM cap | Implemented prependTradeRow with feed.prepend(); trade-card--new modifier removed after 500ms; while loop removes oldest entries beyond 50; escapeHtml and Intl.NumberFormat | Bundled into ADV104 sse.js since both share the same IIFE scope; DOM cap keeps page responsive during long sessions
7 | TICKET-ADV106 | FlorinDLF | Completed | Build sortable, resizable, frozen-header data table on trades.html | Created trades.html and trades.js; click-to-sort with aria-sort toggle and arrow indicators; drag-to-resize on document; position sticky header; demo data with API upgrade path | Resize listeners on document not the handle; no overflow:hidden ancestors so sticky works; status coloring via CSS classes

## Day 8
Day | Ticket | Assignee | Status | Problem | Approach | Observations
8 | TICKET-ADV111 | Lavinia31 | Completed | Vite path aliases need to work at runtime and in the editor | Added missing frontend/jsconfig.json mirroring vite.config.js's alias map; added /stream proxy rule for the future SSE feed | Used relative paths in jsconfig.json instead of the deprecated baseUrl: '.'; verified in the running dev server, not just that it compiles
8 | TICKET-ADV112 | Lavinia31 | Completed | Block protected pages from rendering when the user isn't logged in | Built withAuth(Component) HOC checking AuthContext's user, redirecting to /login otherwise; finished AuthContext (sessionStorage-backed) and apiService's authHeaders()/request() helpers | Confirmed in a real browser: empty sessionStorage always lands on /login; manually seeding the token unlocks the pages
8 | TICKET-ADV113 | Lavinia31 | Completed | A render-time throw unmounts the whole tree to a blank screen | Filled in withErrorBoundary's getDerivedStateFromError/componentDidCatch/render, with a role=alert fallback and a Try again button that resets the error state | Verified with a Playwright script forcing Dashboard to throw; fallback rendered correctly and Try again re-attempts the render
8 | TICKET-ADV114 | Lavinia31 | Completed | Need one reusable sortable/paginated table instead of one-off tables per page | Filled in DataTable.Header/Body/Pagination as a controlled compound component sharing state via context | Existing RTL test had empty TODO assertions; wrote a throwaway test with 5 real assertions to actually prove the behaviour, then deleted it (writing the real RTL assertions belongs to TICKET-ADV125)
8 | TICKET-ADV115 | Lavinia31 | Completed | Need a reusable WebSocket hook with automatic reconnect | useWebSocket keeps socket/retry counter/timer in refs; exponential backoff capped at 30s; resets retry counter on successful reopen | No real backend WS endpoint yet; verified against a local Node WS test server driven by Playwright, then removed the harness. Noted StrictMode + lazy routes double-open on mount in dev only
8 | TICKET-ADV116 | Lavinia31 | Completed | Need an SSE hook for the live trade feed capped at 200 rows | useTradeStream opens EventSource against /api/v1/trades/stream, prepends new trades immutably, caps at 200 | No real backend SSE endpoint yet; verified against a local Node SSE test server (needed CORS header) via Playwright, then removed the harness
8 | TICKET-ADV117 | Lavinia31 | Completed | Search box shouldn't fire an API call per keystroke | useDebouncedSearch settles the value after a pause; also wired the actual data fetch into Trades.jsx (apiService.listTrades) since nothing else owned it | Verified with Vitest fake timers; wiring the real fetch surfaced a pre-existing backend LazyInitializationException on GET /v1/trades, referenced in TICKET-ADV063 (day05) - frontend degrades to empty state correctly on that 500. A temporary EAGER-fetch fix was attempted afterward but rejected as a testing-only shortcut; see tracking-progress/day08/NOTE-lazy-init-blocker-resolved.md
8 | TICKET-ADV118 | Lavinia31 | Completed | Need infinite scroll without polling window.onscroll or recreating the observer per render | useInfiniteScroll splits the loadMore callback (kept fresh via a ref) from the IntersectionObserver (created once); cleanup disconnects it | jsdom can't run IntersectionObserver; verified with Playwright wrapping the real constructor to count create/disconnect calls. Same StrictMode double-create-on-mount caveat as ADV115
8 | TICKET-ADV119 | Lavinia31 | Completed | Trades page re-renders every row on any unrelated state change | New TradeRow.jsx: React.memo with a custom equality on id/status/price/onClick only | Found and fixed a real bug along the way: a literal <tr>/<td> inside DataTable's grid <div> is invalid HTML; fixed with <span style='display:contents'>. Verified render counts with a temporary counter, removed after
8 | TICKET-ADV120 | Lavinia31 | Completed | Dashboard recomputes portfolio value on every render | Wrapped only portfolioValue in useMemo([trades]); left matched/breaks as plain filters, matching the ticket's own guidance against over-memoising cheap calculations | Verified with a mocked stable trades reference (flat count across unrelated re-renders, +1 on real change) and manually against a live SSE test server
8 | TICKET-ADV121 | Lavinia31 | Completed | ADV119's memo never actually holds because onClick is a fresh arrow every render | Added useCallback-wrapped handleSelect in Trades.jsx, swapped inline row markup for <TradeRow> | Tested against a mocked /api/v1/trades response rather than the real backend, since GET /v1/trades was already hitting the pre-existing LazyInitializationException referenced in TICKET-ADV063 (day05). A temporary EAGER-fetch fix was attempted afterward but rejected as a testing-only shortcut; see tracking-progress/day08/NOTE-lazy-init-blocker-resolved.md. Confirmed via render counters that both rows stop re-rendering on unrelated clicks once the handler identity is stable
8 | TICKET-ADV122 | Lavinia31 | Completed | All pages bundled eagerly; Suspense fallback was plain 'Loadingâ¦' text | Added PageSkeleton.jsx (shimmer bars) as the Suspense fallback; removed the unused .loader CSS class - lazy()/Suspense wiring itself already matched the ticket's reference | Verified against a production build; found react-router v7 skips the fallback on in-app <Link> navigation (only shows on direct URL load) - not a bug, documented for later
8 | TICKET-ADV123 | Lavinia31 | Completed | /trades/new needs client-side validation before hitting the network, with correctly-typed numbers | Filled in the Yup schema for every AddTrade field; kept tradeDate as a string (not yup.date()) to match the backend's LocalDate wire format; implemented api.createTrade | Verified against the real backend: empty submit fires 0 requests with 6 alerts; valid submit sends real numbers (not strings); confirmed RHF stays uncontrolled while typing. Known limitation: newly created trades don't show up on /trades because GET /v1/trades hits the pre-existing LazyInitializationException referenced in TICKET-ADV063 (day05). A temporary EAGER-fetch fix was attempted afterward but rejected as a testing-only shortcut; see tracking-progress/day08/NOTE-lazy-init-blocker-resolved.md
8 | TICKET-ADV124 | Lavinia31 | Completed | Need a light/dark toggle where React only owns which theme is active | ThemeProvider reads localStorage first, falls back to prefers-color-scheme for first-time visitors; one effect writes data-theme and persists the choice; added the toggle button | Verified with Playwright across separate browser contexts for OS light/dark defaults, plus persistence across reload
8 | TICKET-ADV125 | Lavinia31 | Completed | No test proves Dashboard's summary cards render correctly through the provider chain | Dashboard.test.jsx with a renderWithProviders helper (Auth/Theme/Router), role-based queries, one numeric assertion | Hit a real jsdom gap: window.matchMedia is undefined, crashing anything wrapped in ThemeProvider; fixed with a small polyfill in the shared test-setup.js
8 | TICKET-ADV127 | Lavinia31 | Completed (optional) | ADV119+ADV121 were implemented but never actually measured before/after | Temporarily reverted the useCallback fix, added a render counter, measured, then restored both files to their committed state | Render counts: both rows re-rendered on every click before the fix (climbing every time), zero re-renders after - confirmed both via Playwright scripted counts and the real React DevTools Profiler

## Day 9
Day | Ticket | Assignee | Status | Problem | Approach | Observations
9 | TICKET-ADV128 | pshavela | Completed | Add Kafka topics for event-based messaging | Kafka topics in dev mode are defined manually via the docker container
9 | TICKET-ADV129 | pshavela | Completed | Emit a TradeEvent kafka topic | Use KafkaTemplate<String, TradeEvent> to publish events | Define the tradeRef as the key so all events for the same trade hash to the same partition and maintain ordering
9 | TICKET-ADV130 | pshavela | Completed | Define the TradeEvent kafka topic | Nothing to do
9 | TICKET-ADV131 | pshavela | Completed | Implement a Consumer for trade events to trigger reconciliation | Just implement logging | We will use a custom triggering mechanism which involves a single POST endpoint, not on every trade add
9 | TICKET-ADV132 | pshavela | Completed | Implement a Consumer for audit events and persist to audit_log table | Similar to ReconConsumer, implement an onTradeEvent subscription method
9 | TICKET-ADV133 | pshavela | Completed | Implement a Consumer for system alert events | Just log in dev mode
9 | TICKET-ADV134 | pshavela | Completed | A DLQ error Handler which publishes on message failures | Define a DefaultErrorHandler with Exponential backoff which publishes to a custom -dlq topic after three failed attempts | The -dlq topic must have the same number of partitions as the primary and the DefaultErrorHandler will publish to all partitions
9 | TICKET-ADV135 | pshavela | Completed | Implement a Retry strategy with backoff for messages | Done in the previous ticket using ExponentialBackoff
9 | TICKET-ADV136 | Lavinia31 | Completed | DlqConsumer/DlqAdminController did not exist; the guide references the wrong Kafka header for the failure reason on a DeadLetterPublishingRecoverer record | Added DlqMessage entity+table, DlqConsumer (fixed to KafkaHeaders.DLT_EXCEPTION_MESSAGE, not EXCEPTION_MESSAGE), DlqAdminController with GET list + POST replay, ADMIN-only via @PreAuthorize | Forced a real duplicate-eventId failure and watched it retry then land on the DLQ, then replayed it; also found and fixed a separate bug where @PreAuthorize denials returned 500 instead of 403
9 | TICKET-ADV137 | Lavinia31 | Completed | TradeAggregator.rebuild(tradeRef) did not exist; the guide assumes a different AuditLogEntry shape (JsonNode/getOperation) than this codebase actually has (String/getEventType) | Implemented rebuild() folding audit_log events ordered by event_timestamp (not eventId - not monotonic); CREATED/UPDATED set state, CANCELLED clears it | Covered with 3 unit tests matching the ticket's own scenarios; had no caller anywhere until wired into a real endpoint in ADV138
9 | TICKET-ADV138 | Lavinia31 | Completed | GET /v1/audit/trades/{tradeRef}/events was a stub always returning an empty list | Wired the real query (same as the sibling history() method); added explicit @PreAuthorize; added a bonus /rebuild endpoint exposing ADV137's TradeAggregator | Verified live: ADMIN 200, TRADER 403, unauthenticated 403; /rebuild matched the real trades row for a live trade and 404'd for a cancelled one
9 | TICKET-ADV139 | Lavinia31 | Completed | No kafka_consumer_*/kafka_producer_* metrics were exposed on /actuator/prometheus | Enabled management.metrics.binders.kafka.enabled: true; skipped the guide's other suggested property (metric.reporters=KafkaClientMetrics), which crashes the app on startup | Verified metrics appear after publishing events; found this Kafka client version exposes them under kafka_consumer_fetch_manager_*, not the bare names the ticket names
9 | TICKET-ADV140 | Lavinia31 | Completed | No consumer-lag-by-topic Grafana panel existed | Added a Kafka health row to the existing Day 6 dashboard with a lag panel (yellow@100/red@1000), using the real fetch_manager-prefixed metric name | Verified live via a direct Prometheus API query and a screenshot of the rendered panel
9 | TICKET-ADV141 | Lavinia31 | Completed | No produced-vs-consumed throughput panel existed | Added a panel with two rate() series next to the lag panel in the same row | Verified with real traffic: consumed came out ~2x produced, which is correct - trade-events has two independent consumer groups
9 | TICKET-ADV142 | Lavinia31 | Completed | DLQ count Stat panel did not exist; the pre-existing KafkaDlqGrowing alert pointed at a nonexistent metric name and was missing a description annotation | Added the Stat panel; renamed/retargeted the alert to KafkaDlqMessages, added the missing description | Verified live end to end: forced a DLQ message, watched the panel show 1 and the alert transition to firing with the interpolated description
9 | TICKET-ADV143 | Lavinia31 | Completed | No Testcontainers test proved the producer-to-consumer-to-DB pipeline; Testcontainers itself could not start a container in this environment | Wrote KafkaPipelineIT (adapted TradeEvent construction to the real API, added the missing awaitility dependency); fixed Testcontainers by bumping 1.20.3 to 1.21.4, resolving a real Docker Desktop npipe incompatibility | 100 events through a real broker in 27.65s; also unblocked the two pre-existing Testcontainers tests that were failing before this bump
9 | TICKET-ADV144 | Lavinia31 | Completed | No test proved a failing consumer actually routes to the DLQ; the guide mocks a ReconciliationEngine method that is not wired into this codebase's real consumer at all | Wrote DlqRoutingIT forcing a real failure (duplicate eventId) instead of mocking a nonexistent dependency; fixed a deserializer bug in the raw assertion consumer (missing default type) | Full backend suite green, 28/28 tests, after this and the Testcontainers fix